## Sheet1
Task | Owner | Assigned | Due | Status | Done | Time Spent | Notes
1.User should be able to upload an image | Tasin | 2018-05-09 | 2018-05-09 | 100% | ✓ | 5 hours
2.IBM Visual Recognition should be able to receive an Image and send an response regarding face Infomration in JSON | Hussain | 2018-05-10 | 2018-05-10 | 100% | ✓ | 3 hours
3.User should be able to get the total number of faces in the image | Tasin | 2018-05-11 | 2018-05-11 | 100% | ✓ | 1 hour
4. Users should be able to get the average age of each user | Hussain | 2018-05-11 | 2018-05-11 | 100% | ✓ | 30 Mins
5. Users should be able to get the gender of each user | Hussain | 2018-05-12 | 2018-05-12 | 100% | ✓ | 30 Mins
6.IBM Text-to-audio service should be able to receive text and send an audio file representing the text | Tasin | 2018-05-12 | 2018-05-12 | 100% | ✓ | 2 hours
7.User should be able to listen to audio consisting of data from user stories 3,4,5 | Hussain | 2018-05-12 | 2018-05-13 | 70% | INCOMPLETE